Indiana Beta Sigma Phi

State Council

State Fun Day Guidelines

Revised September 2024

FHA COMMITTEE 2024

Bea Smith Co-Chair

Peggy Wood C0-Chair

Brenda Gonzales

Ava Kiefer

Teressa Meredith

Yvonne Nace

Peggy Osmon

| Timeline Guide for State Fun Day |  |  |
| --- | --- | --- |
| Time | Item | complete |
| 1-2 years before | Submit bid to FHA |  |
| 1-2 years before | Secure venue/hotel |  |
|  | Create Theme |  |
|  | Designate Chairperson(s) |  |
|  | Designate Secretary and Treasurer |  |
|  | Designate Registration person |  |
|  | Set Budget |  |
|  | Form committees as needed |  |
|  | Create Flyer/skit for presentations at State Events Send Flyer to Website. |  |
| Year before event | Meet with board at events for updates. You may submit a form for a Ways and Means Booth to help raise money for your Event. |  |
| 1 Event before your event | Board must approve registration packet before emailing and or mailing. |  |
| Month before | Complete registration packets |  |
| 30 days before | Registration deadline- registration deadline can be extended by the Host City but Not Ways & Means booths. |  |
| 14 days before | Send/email registration list to State President, Vice President & State Treasurer |  |
| Day before | Meet with Executive Board before your event to give board their registration packets (if applicable). If there are packets and they are counted by the State Vice President and State Treasurer, the host retains the packets until the event’s registration. |  |
| No later than month after | Send check to state board if you borrowed start up monies. |  |

Next Event after your Event	      Give Final Report including Financial Report to Board & Membership.

| Checklist for the Day of the Event |  |
| --- | --- |
| State Fun Day |  |
| Registration | Staffing –2 of committee to do registration. Registration time TBD by Committee |
|  | Microphone, if needed |
|  | Name tags, if needed |
|  | Decorations, if needed |
|  | Door Prizes (Optional) |
| President's Suite | Pay for 1 night – Check with President to see if she wants to come in early and pay for the extra night (which would be Thursday) as State Fun Day should be paying for Friday night in the budget for Fun Day. If venue doesn’t have a reasonable suite, do a king room, then consult with the President for her storage needs for the weekend. |
| Next event after your event | Give final report including financial report to Executive Board and Membership. |

AGENDA FOR STATE FUN DAY

REGISTRATION	TBD BY COMMITTEE

FUN TIME - 		TBD COMMITTEE

LUNCH			TBD COMMITTEE

GOOD PRACTICE:  FUN TIME TO FINISH AFTER LUNCH TILL AROUND 3:00 – 3:30 PM

THIS LEAVES TIME FOR SISTERS TO SHOP, VISIT, HAVE DINNER, ETC.

Chairman/Co-Chairman

- NOTE:  Most Hotels, Event Centers are now requiring upfront deposits.

- Check with event space on insurance requirements

- Conduct all planning meetings (set as needed).

- Secure the location/venue for the event with approval of committee.

- Set up a budget with committee approval.   Review attendance from past events to help set budget.

- Chair/Co-Chair may request a loan from the State Executive Board (check with the State Treasurer for amount available) to be paid back no later than one month after the event.

- Generally, the host of State Day will see to the hotel reservations for the State President.  The event host should make sure that the State Day host has reserved two (2) nights for the State President.  The State Fun Day Committee are responsible for paying for one nigh stay in the hotel for the State President.  Make sure that you have included this one-night stay in your budget.

- Designate one person to be the liaison with the hotel if it is not the Chair of the event.  This person should make sure a suite has been reserved for the President (check with President if she wants to come in early and pay for the extra nights herself).  In the event the Board Meeting can be held in the President’s Suite, the hotel staff needs to set it up for her on the morning of the meeting.

- Generally the host of State Day will see to the hotel reservations for the State President.  The event host should make sure that the State Day host has reserved two (2) nights for the State President.  The State Fun Day Committee are responsible for paying for one-night stay in the hotel for the State President.  Make sure that you have included this one-night stay in your budget.

- Follow timeline guide to make sure tasks are accomplished. Check with hotel if we can bring food/drink or if the hotel restaurant is available for lunch in the Board room.

- Determine the theme of your event and if your event will or will not have:

  - Registration Gifts/mementos

  - Individual table gifts

  - Type of decorations/centerpieces

Secretary

- The Secretary shall bring to first State Board Meeting prior to your Event the names, addresses, telephone numbers, and email addresses of event board (Chair, Co-Chair, Treasurer, Secretary, Registration Chair and Ways & Means Chair) for all Board Members and FHA Chairman.

- Keep minutes of each meeting to be given to all Board Members @ each reporting time and to FHA Chairman or emailed to Board members before the next reporting time.

- Submit to Website:  Name, Address, Telephone number, and email address of Chairman/Co-Chairman of the Event.  Also submit a Flyer to Website.

- Work with the State Secretary to determine who will submit Registration Packet to website.

Treasurer

- The Treasurer is responsible for opening the checking account.  If possible, the bank account shall be known as:  Indiana Beta Sigma Phi State Council Day Fund. Good practice is Checking account should have two (2) signers on account/only one on check.

- All deposits are to be made by the Treasurer upon receipt of the funds. Good practice is to make copies of check deposit and checks

- All entries in the ledger shall be made immediately by the Treasurer so the books will be ready for inspection for audit at any time upon request by the Chairman/Co-Chairman of the event or the Executive Board.

- All bills should be paid including loan from State, if borrowed, and the books closed as soon as possible after the close of the event.

- Prepare closing financial statement which will be emailed to the State President and to the State FHA Chairman.

Registration Chair/Committee

- Complete Registration forms and accompanying documents are to be given to State Secretary at prior State event for her to email.

- Make one copy of all checks to keep with the registration form before giving Treasurer actual checks.

- A spread sheet provided by the State Board shall be used to keep your registration orderly, keeping the delegates, non-delegates, and guests separate.  Registration Template is on Website and a sample is included in this packet.  All columns need to be totaled including the Degree Columns showing number of Chapters registered in each degree.

- As registrations are received from the chapters, begin the process which will allow you to provide delegate listings, non-delegate listings, labels for registration packets, etc.   Entering the names into your system as they come in, will eliminate any last-minute typing and also allow time to check for errors such as spelling, et.

- A list of everyone registered should be emailed to the State President, Vice President, and Treasurer as soon after the registration deadline as possible (no later than two (2) weeks prior to the event).  If there is a change in registration, current copies need to be emailed to State Vice President and Treasurer on Monday prior to Event.

- Attach the labels to the registration packets.  Labels should include name, chapter, city, and table numbers (if used). Packets should include - program books, name tags, and any other pertinent information.

- File the packets by city, chapter, and then alphabetically, using the same method as the registration listings.  These packets need to be taken to the Board Meeting at the Event for Vice President and

Treasurer to count. The number of packets must match registration count.  Officers are given their packet at this time (unless they are Delegates).

- The distribution of registration packets of delegates will be handled by the State Vice President and the State Treasurer.  All others will be handled by two members of the committee.

- Delegates must pick up their own packets unlike non delegates. If unable to attend, the delegate’s packet can be picked up from the State Vice President after the business meeting.

- A convenient place should be reserved for the registration of delegates and non-delegates.  If room is available, tables could be set up to list two groups at the delegate and non-delegate tables, using letters designating cities from A-H and I-Z.  This method is generally used in order to speed up registration.

- State Project (not State Project Committee) needs to have a Registration Packet for the Representative attending.

Registration Mailing

- Registrations Packets must be approved by the state board one Event prior.  Once Registration Packet is approved it should be emailed to State Secretary.

- Registration Form needs to be a Single page.

- Sample Official registration form and Ways & Means form are included in this packet.  If the Registration packet must be resubmitted to the Executive Board for approval.

- If changes are made to Registration packet after Board approval it must be emailed to Board President for re-approval.

Other items to include

- Ways & Means rules (must be current rules from State Ways & Means Chairman)

- Directions/Map

- Timeline of events

- Hotel information

- Any other information the host would like to include

Program Books/Name Tags

- Program books and name tags should coordinate with the theme.  They should be included in the registration packet.

- The program book should include:

  - Agenda – Times, location, speakers

  - Opening & Closing Rituals

  - Menu

  - Grace

  - Event committee

  - Attendance summary – List all degrees including Torch Bearer

  - Special thank you section (if needed)

  - Anything else you would like to add in

- The name tag must include

  - Name (Emphasize First Name and Readability)

  - Chapter

  - City