Indiana Beta Sigma Phi

State Council

State Day Guidelines

Revised September 2024

FHA COMMITTEE 2024

Bea Smith Co-Chair

Peggy Wood – Co-Chair

Brenda Gonzales

Laura Hopkins

Ava Kiefer

Teressa Meredith

Yvonne Nace

Peggy Osmon

| Timeline Guide for State Day |  |  |
| --- | --- | --- |
| Time | Item | complete |
| 1-2 years before | Submit bid to FHA |  |
| 1-2 years before | Secure venue/hotel |  |
|  | Create Theme |  |
|  | Designate Chairperson(s) |  |
|  | Designate Secretary and Treasurer |  |
|  | Designate Ways & Means person |  |
|  | Designate Registration person |  |
|  | Set Budget |  |
|  | Form committees as needed |  |
|  | Create Flyer/skit for presentations at State Events Send Flyer to Website. |  |
| Year before event | Meet with board at events for updates. You may submit a form for a Ways and Means Booth to help raise money for your Event. |  |
| 1 Event before your event | Board must approve registration packet before emailing and or mailing. |  |
| Month before | Complete registration packets |  |
| 30 days before | Registration deadline- registration deadline can be extended by the Host City but Not Ways & Means booths. |  |
| 14 days before | Send registration list to State President, Vice President & State Treasurer |  |
| Day before | Meet with Board final time - give board their registration packets. (Board members who are Delegates must pick up their packet at Registration.) Registration Chairman brings all Registration packets to the meeting to be counted by the State VP and Treasurer. Host retains registration packets until the event’s registration time. |  |
| No later than month after | Send check to state board if you borrowed start up monies. |  |

| Checklist for the Day of the Event |  |
| --- | --- |
| State Day |  |
| Registration | Next Event after your Event give Final Report including Financial Report to Board & Membership. Staffing: State Vice President and State Treasurer –Delegates, 2 of committee to do non-delegates – Registration time 9:00 – 10:30 AM |
| Way & Means | Staffing - event Ways and Means chair - others as needed - Someone from Committee needs to be in Ways & Means room at all times. Setup time 9:00 AM, Booths open 9:30 – 11:00 AM |
|  | Podium at Head table w/ microphone |
|  | Floor microphone for Business Meeting (if possible, with hotel and budget) |
|  | Name tags |
|  | Decorations |
|  | Door Prizes (Optional) |
| President's Suite | Pay for 1 night – Check with President to see if she wants to come in early and pay for the extra nights. If venue doesn’t have a reasonable suite, do a king room, then consult with the President for her storage needs for the weekend. If Board meeting will be held in the President’s suite, ask if the hotel will set up table and chairs. |
| Board Room | Needed unless meeting can be held in President’s Suite. |

Chair/Co-Chair

- NOTE:  Most Hotels, Event Centers are now requiring upfront deposits.

- Check with event space on insurance requirements

- Conduct all planning meetings (set as needed).

- Secure the location/venue for the event with approval of committee.

- Set up a budget with committee approval.   Review attendance from past events to help set budget.  Budget must include – A Suite for President for one (1) night, board meeting room (if not complimentary) unless Board Meeting can be held in the President’s Suite. If venue doesn’t have a reasonable suite, a a king room, then consult with the President for her storage needs for the weekend.

- Chair/Co-Chair may request a loan from the State Executive Board (check with the State Treasurer for amount available) to be paid back no later than one month after the event.

- Generally the host of State Day will see to the hotel reservations for the State President.  The event host should make sure that the State Day host has reserved two (2) nights for the State President.  The State Fun Day Committee are responsible for paying for one-night stay in the hotel for the State President.

- Designate one person to be the liaison with the hotel if it is not the Chair of the event.  This person should make sure a suite has been reserved for the President (check with President if she wants to come in early and pay for the extra nights herself).  In the event the Board Meeting can be held in the President’s Suite, the hotel staff needs to set it up for her on the morning of the meeting.

- Follow timeline guide to make sure tasks are accomplished. Check with hotel if we can bring food/drink or if the hotel restaurant is available for lunch in the Board room.

- Determine the theme of your event and if your event will or will not have:

  - Registration Gifts/mementos

  - Individual table gifts

  - Type of decorations/centerpieces

  - Large door prizes and number   Please consider the time it will take to give out the number of door prizes you decide on.

These items can have separate committees if necessary.

Secretary

- The Secretary shall bring to first State Board Meeting prior to your Event the names, addresses, telephone numbers, and email addresses of event board (Chair, Co-Chair, Treasurer, Secretary, Registration Chair and Ways & Means Chair) for all Board Members and FHA Chairman.

- Keep minutes of each meeting to be given to all Board Members @ each reporting time and to FHA Chairman or emailed to Board members before the next reporting time.

- Submit to Website:  Name, Address, Telephone number, and email address of Chairman/Co-Chairman of the Event.  Also submit a Flyer to Website.

- Work with the State Secretary to determine who will submit Registration Packet to Website.

Treasurer

- The Treasurer is responsible for opening the checking account.  If possible, the bank account shall be known as:  Indiana Beta Sigma Phi State Council Day Fund. Good practice is Checking account should have two (2) signers on account/only one on check.

- All deposits are to be made by the Treasurer upon receipt of the funds. Good practice is to make copies of check deposit and checks

- All entries in the ledger shall be made immediately by the Treasurer so the books will be ready for inspection for audit at any time upon request by the Chairman/Co-Chairman of the event or the Executive Board.

- All bills should be paid including loan from State, if borrowed, and the books closed as soon as possible after the close of the event.

- Prepare closing financial statement which will be presented to the State Board by the Chair/Co-Chair (need one copy for each State Board member and enough copies to be put in the state mailing). Also, a copy for the State FHA Chairman.

Registration Chair/Committee

- Complete Registration forms and accompanying documents to give to State Secretary at prior State event for her to email.

- Make one copy of all checks to keep with the registration form before giving Treasurer actual checks.

- A spread sheet provided by the State Board shall be used to keep your registration orderly, keeping the delegates, non-delegates, and guests separate.  Registration Template is on Website and a sample is included in this packet.  All columns need to be totaled including the Degree Columns showing number of Chapters registered in each degree.

- As registrations are received from the chapters, begin the process which will allow you to provide delegate listings, non-delegate listings, labels for registration packets, etc.   Entering the names into your system as they come in, will eliminate any last minute typing and also allow time to check for errors such as spelling, et.

- A list of everyone registered should be emailed to the State President, Vice President, and Treasurer as soon after the registration deadline as possible (no later than two (2) weeks prior to the event).  If there is a change in registration, current copies need to be emailed to State Vice President and Treasurer on Monday prior to Event.

- Attach the labels to the registration packets.  Labels should include name, chapter, city, and table numbers (if used). Packets should include - program books, name tags, and any other pertinent information.

- File the packets by city, chapter, and then alphabetically, using the same method as the registration listings.  These packets need to be taken to the Board Meeting at the Event for Vice President and

Treasurer to count. The number of packets must match registration count.  Officers are given their packet at this time (unless they are Delegates).

- The distribution of registration packets of delegates will be handled by the State Vice President and the State Treasurer.  All others will be handled by two members of the committee.

- Delegates must pick up their own packets unlike non delegates. If unable to attend, the delegate’s packet can be picked up from the State Vice President after the business meeting.

- A convenient place should be reserved for the registration of delegates and non-delegates.  If room is available, tables could be set up to list two groups at the delegate and non-delegate tables, using letters designating cities from A-H and I-Z.  This method is generally used in order to speed up registration.

- State Project (not State Project Committee) needs to have a Registration Packet for the Representative attending.

Registration Mailing

- Registrations Packets must be approved by the state board one Event prior.  Once Registration Packet is approved it should be emailed to State Secretary.

- Registration Form needs to be a Single page.

- Sample Official registration form and Ways & Means form are included in this packet.  If the Registration packet must be resubmitted to the Executive Board for approval.

- If changes are made to Registration packet after Board approval it must be emailed to Board President for re-approval.

Other items to include

- Ways & Means rules (must be current rules from State Ways & Means Chairman)

- Directions/Map

- Timeline of events

- Hotel information

- Any other information the host would like to include

Program Books/Name Tags

- Program books and name tags should coordinate with the theme.  They should be included in the registration packet.

- The program book should include:

  - Agenda – Times, location, speakers

  - Opening & Closing Rituals

  - Menu

  - Grace

  - Event committee

  - Attendance summary – List all degrees including Torch Bearer

  - Special thank you section (if needed)

  - Anything else you would like to add in

- The name tag must include

  - Name (Emphasize First Name and Readability)

  - Chapter

  - City

Ways and Means Chair/Committee

- This Committee is governed by the rules set up by the State Ways and Means Committee. Please obtain current copy from State Ways & Means Chairman.

- Determine if the venue will charge extra to setup Ways & Means tables.  If so, that charge should be passed on to chapters having a booth.

- Create Ways & Means form for the Registration packet.  (Sample in included in this packet).

- Choose the theme for Ways & Means, keeping in mind the general theme of the event.

- Inform the Event Chair/Co-Chair of the number of booths registered so they can confirm space with the venue.  The Event Chair/Event Ways & Means Chair shall identify the location of each booth.

- Confirm whether table coverings will be provided by event site.

- Make a list of booths by chapter name and the item (either selling or shares).  List should be emailed to Event Chair, Event Ways & Means Chair, Next Event Ways & Means Chair, and the State Ways & Means Chair two weeks prior to the event.

- Only chapters registered for the event may have a Ways and Means booth.  Copy of Chapter Registration with copy of check attached must be with the Ways and Means Form. Confirm with Registration Chair to ensure chapter is registered prior to confirming booth assignment to chapter submitting bid.  State Project (not State Project Committee) is to have a booth and will be taken care of by the representative attending the Event.

- State Project Committee, Secondary Project, Membership, State Historian, State Event Hosts (3 state events prior to their event and one at their event), Previous State Event if needed, Officers Reception, and Website are guaranteed a booth IF they mail their request with copy of registration form and check.

- On the day of the event, you or someone from your Committee direct chapters to their booths.  Someone from the Ways & Means Committee should be in the room at all times.

- All items must be given away at the luncheon.

- The Event chairman and the State Ways and Means Chairman shall stop by each booth and draw the winning & back up ticket, putting them in envelopes marked winner and back up.  Envelopes must have:

- Chapter’s name

- Item to be given

- Color of ticket & table number

- If a split the pot, the amount to be given away

- Number each application as they come in the mail in case too many applications or duplicates are submitted.

State Day Events

- All events should be cohesive with the State Day theme.

Sunday

- Registration  9:00 – 10:30

- Ways & Means Setup 9:00   Ways & Means selling  9:30 – 11:00

- Luncheon

Choose menu and entertainment if desired

State Project guest speaks

Ways & Means given out

Break	10 – 15 minute break before the Business meeting starts

- Always check with President for Agena for State Day business meeting

- Door Prizes (if applicable)

- Closing Ritual